## ADDIE Model Template
ADDIE Model Template
Instructions: 1. Fill in the To do column with your tasks and deliverables for each stage of ADDIE. 2. Update each column.
PROJECT NAME
Stages |  | To do |  | Status | Progress made | Start Date | Due Date | Who | Notes
A | ANALYSIS | Tasks | Identify learning objectives: Determine what the learners need to know or be able to do by the end of the course. | To do | 50% | 2024-03-06 | 2024-03-17 | Jane
|  |  | Assess learner characteristics: Gather information about the target audience, including their existing knowledge, skills, learning preferences, and any specific needs. | In progress | 20%
|  |  | Analyze content requirements: Identify the content that needs to be covered to meet the learning objectives. | Done | 70%
|  |  | Define learning environment: Determine the physical or digital environment where the learning will take place, including any tools or platforms to be used. |  | 0%
|  |  | Establish constraints: Identify any constraints that may affect the training, such as budget, timelines, or technological limitations. |  | 0%
|  | Deliverables | Training needs analysis report: A document detailing the learning objectives, target audience characteristics, and specific training needs. |  | 0%
|  |  | Learner analysis report: Profiles of the target audience, including their prior knowledge, skills, learning preferences, and any special considerations. |  | 0%
|  |  | Environmental and resource analysis: An overview of the available resources and technology, as well as any constraints that may impact the training program. |  | 0%
D | DESIGN | Tasks | Outline the course structure: Develop a blueprint of the course, outlining modules, lessons, and the flow of content. |  | 0%
|  |  | Select instructional strategies: Choose teaching methods and strategies that best fit the content and learner characteristics, such as storytelling, simulations, or problem-based learning. |  | 0%
|  |  | Design assessments: Create assessments that align with the learning objectives to measure learner progress and understanding. |  | 0%
|  |  | Storyboarding: Develop storyboards for digital content, detailing screen layouts, text, images, and interactions. |  | 0%
|  |  | Plan learning activities: Design activities that engage learners and support the instructional strategies, such as discussions, projects, or hands-on exercises. |  | 0%
|  | Deliverables | Instructional design plan: A comprehensive document outlining the course structure, including modules, lessons, and the sequence of content. |  | 0%
|  |  | Storyboard documents: Visual representations of digital courses, including screen layouts, text, graphics, and instructions for interactive elements. |  | 0%
|  |  | Assessment strategy: A plan for how learning will be assessed, including types of assessments, criteria for success, and alignment with learning objectives. |  | 0%
D | DEVELOPMENT | Tasks | Create content: Produce the learning materials, including writing scripts, recording videos, developing slides, or coding interactive elements. |  | 0%
|  |  | Build assessments: Develop the assessment tools, ensuring they are valid and reliable measures of learning. |  | 0%
|  |  | Test interactivity: Ensure all interactive elements function as intended, including quizzes, simulations, and any software or tools used in the learning process. |  | 0%
|  |  | Review and revise: Conduct a thorough review of the materials for accuracy, clarity, and alignment with learning objectives. Revise as needed. |  | 0%
|  | Deliverables | Course materials: All created content, including slide decks, videos, reading materials, and interactive elements. |  | 0%
|  |  | Assessment tools: Developed assessments ready for ready for implementation, such as quizzes, tests, projects, or performance tasks. |  | 0%
|  |  | Technical specifications: Documentation of any technical requirements and configurations for the learning environment, including software, hardware, and platform details. |  | 0%
I | IMPLEMENTATION | Tasks | Prepare the learning environment: Set up the physical or digital space where the training will occur, ensuring all necessary tools and technologies are in place. |  | 0%
|  |  | Train facilitators: If applicable, provide training for instructors or facilitators on the course content and how to use any tools or platforms. |  | 0%
|  |  | Communicate with learners: Inform learners about the course details, including objectives, schedule, and expectations. |  | 0%
|  |  | Launch the course: Make the course available to learners, providing any necessary support to access and navigate the materials. |  | 0%
|  | Deliverables | Implementation plan: A detailed guide for rolling out the training, including timelines, responsibilities, and procedures for accessing the course. |  | 0%
|  |  | Facilitator guides: If applicable, comprehensive guides for instructors or facilitators, including lesson plans, discussion points, and how to use course technologies. |  | 0%
|  |  | Learner instructions: Clear instructions for learners on how to access and navigate the course, including login information, course navigation, and support contacts. |  | 0%
E | EVALUATION | Tasks | Gather feedback: Collect feedback from learners on the effectiveness of the course and their learning experience. |  | 0%
|  |  | Assess learning outcomes: Evaluate learner performance on assessments to determine if learning objectives were met. |  | 0%
|  |  | Analyze course data: Review data from the learning platform for insights into learner engagement and behavior. |  | 0%
|  |  | Make improvements: Use the feedback and data collected to refine and improve the course materials and structure for future iterations. |  | 0%
|  | Deliverables | Evaluation report: A document summarizing the feedback from learners, assessment results, and any data on learner engagement and satisfaction. |  | 0%
|  |  | Lessons learned document: A reflection on the training program's successes and areas for improvement, based on the evaluation findings. |  | 0%
|  |  | Recommendations for future iterations: Suggestions for revisions to the course content, structure, or delivery based on the evaluation results, aimed at enhancing future offerings. |  | 0%

## Simple ADDIE Model Template
ADDIE Model Template
Instructions: 1. Fill in the objectives, tasks, and deliverables for each stage of ADDIE. 2. Update the progress.
PROJECT NAME
ADDIE stage | A | D | D | I | E
| ANALYSIS | DESIGN | DEVELOPMENT | IMPLEMENTATION | EVALUATION
Objective | Identify the learners' needs, define the learning goals, and understand the context in which the training will occur. | Plan the instructional strategy, structure the content, and design the learning experience to meet the identified needs. | Create or assemble the instructional materials, develop the assessments based on the design specifications. | Deliver or distribute the training to the intended audience and support their learning process. | Assess the effectiveness of the training in achieving its learning objectives and identify areas for improvement.
Tasks | Identify learning objectives Assess learner characteristics Analyze content requirements Define learning environment Establish constraints | Outline the course structure Select instructional strategies Design assessments Storyboarding Plan learning activities | Create content Build assessments Test interactivity Review and revise | Prepare the learning environment Train facilitators Communicate with learners Launch the course | Gather feedback Assess learning outcomes Analyze course data Make improvements
Deliverables | Training needs analysis report Learner analysis report Environmental and resource analysis | Instructional design plan Storyboard documents Assessment strategy | Course materials Assessment tools Technical specifications | Implementation plan Facilitator guides Learner instructions | Evaluation report Lessons learned document Recommendations for future iterations
Progress | 50% | 0% | 0% | 0% | 0%