## Change Management Comms Plan
Change Management Communication Plan Template
Instructions
1. In the first column, clearly define the goals the communication plan should achieve. 2. In the second column, list the groups affected by the change and map what each group must know and when they must know it. 3. In the third column, include the communication plan's key messages, which should answer the questions employees are most likely to ask. 4. In the fourth column, outline which channels you will use to deliver key messages, for what purpose, and who should deliver each message. 5. In the fifth column, list the mechanisms you'll use to gather employee input, along with the intended outcome of each mechanism. 6. In the sixth column, detail the support resources you'll provide to help employees navigate the change, as well as the purpose of each resource. 7. In the final column, outline possible communication challenges and how you plan to address each one.
Executive summary | (Clearly explain what the change is, why it's happening, and how it connects to the organization’s broader goals.)
Goals and objectives |  | Stakeholder mapping |  | Key messages | Communication channels |  | Feedback and measurement |  | Support resources |  | Risk management and contingency planning
Goal 1 | Objectives of goal 1 (raising awareness) | Who: | Executives | Most day-to-day work will stay the same at first, with adjustments phased in over the next 90 days. | Channel(s): | Email and intranet | Mechanism: | Employee survey | Resource: | FAQ | Challenge: | Resistance
|  | What to know | Strategic insights (business reason, expected outcomes, success metrics) |  | Purpose: | Overall vision and intention of the change | Intended outcome: | Gauge staff sentiment, identify risks, determine how to improve adoption. | Purpose: | Answer common employee questions clearly and consistently to reduce uncertainty, align messaging, and speed up change adoption. | Solution: | Involve staff early, listen to and address specific concerns. Back it with clear benefits, targeted training, manager-led support, and steady feedback loops.
|  | When to know it | 2-4 weeks before announcing the change |  | Responsible party/parties: | Senior executives
Goal 2 | Objectives of goal 2 | Who: |  |  | Channel(s): |  | Mechanism: |  | Resource: | FAQ | Challenge:
|  | What to know |  |  | Purpose: |  | Intended outcome: |  | Purpose: |  | Solution:
|  | When to know it |  |  | Responsible party/parties:
Goal 3 | Objectives of goal 3 | Who: |  |  | Channel(s): |  | Mechanism: |  | Resource: |  | Challenge:
|  | What to know |  |  | Purpose: |  | Intended outcome: |  | Purpose: |  | Solution:
|  | When to know it |  |  | Responsible party/parties:
Goal 4 | Objectives of goal 4 | Who: |  |  | Channel(s): |  | Mechanism: |  | Resource: |  | Challenge:
|  | What to know |  |  | Purpose: |  | Intended outcome: |  | Purpose: |  | Solution:
|  | When to know it |  |  | Responsible party/parties:
Goal 5 | Objectives of goal 5 | Who: |  |  | Channel(s): |  | Mechanism: |  | Resource: |  | Challenge:
|  | What to know |  |  | Purpose: |  | Intended outcome: |  | Purpose: |  | Solution:
|  | When to know it |  |  | Responsible party/parties: